## Slide 1: Simple Touch Prediction With Built-In IMUs Intermediate Presentation
Felix Bühler, Benedict Steuerlein
FaPra Machine Learning and Computer Vision for HCI | Pfaffenwaldring 5a | 08.01.19
Notes: We are F and B an our subject is Simple Touch Prediction with built in IMUs

## Slide 2
Current Status
Carried out study with 18 participants
Still need 2 participants!

## Slide 3
Current Status
Preprocessing
Segmentation
Remove duplicates
Sensor data alignment
Data generator
Model training
For 18 participants on one phone:
  12 GB in RAM
We will have 20 participants and four phones:
  52 GB in RAM
Data generator reading hdf5 files from hard drive
  Slower, but almost no RAM utilization
Limited by hardware!

## Slide 4
Current Status
Preprocessing
Segmentation
Remove duplicates
Sensor data alignment
Data generator
Model training
Trained our first model
  Only for Nexus 5X
  18 participants (13 train – 5 test)
After 240 epochs (10 days, 5h)
  Euclidean distance between actual touch and predicited touch: 5.389 mm
Hint from Sven that our loss function is calculating the mean instead of RMSE (thank you, stackoverflow)
Repeat training with correct loss function

## Slide 5
Model Accuracy
This can’t be right
Pixel
Epochs

## Slide 6
2018
Today
Nov
Dez
Jan 2019
Feb
8 Tage
11/6/2018
Discussion
11/13/2018
15 Tage
11/13/2018
11/27/2018
Android App
14 Tage
11/28/2018
Data Collection Study
12/11/2018
29 Tage
12/11/2018
1/8/2019
Network Training
8 Tage
1/8/2019
Discussion
1/15/2019
15 Tage
1/15/2019
1/29/2019
Evaluation
8 Tage
1/29/2019
Paper Revision
2/5/2019
71 Tage
11/27/2018
2/5/2019
Agenda
Writing Paper
Notes: Right no we are on schedule.
Finished implementing the study app.
From now on, we want to conduct the study

## Slide 7
Questions
Currently only using window size of 150ms (50 samples) due to data.
What could be wrong?
Should we switch to classification instead of regression?